## Project Summary
Paving Contractor Job Cost Summary
Enter project information below. Every KPI in the lower table is calculated from the other sheets.
Project Name
Client
Project Address
Estimator
Project Manager
Contract Amount
Original Estimate Date
Start Date
Completion Date
Project Type
Notes
Summary KPIs
Metric | Estimated | Actual | Variance | Notes
Revenue |  |  |  | Overtype Actual if approved change orders moved the contract amount.
Direct Job Cost |  |  |  | Totals from the Estimate vs Actual cost codes.
Gross Profit |  |  |  | Revenue less direct job cost. Company overhead is not deducted here.
Gross Margin % |  |  |  | Gross profit divided by revenue — margin, not markup.
Total Labor Hours
Asphalt Tons
Paving Hours
Tons Per Hour
Truck Hours
Paving Days
Shaded cream = you enter this. Shaded grey = calculated, don't overtype.
Gross margin is gross profit divided by revenue. Markup is profit divided by cost — the two are not interchangeable.

## Estimate vs Actual
Estimate vs. Actual Job Costs
Enter the original estimate once and leave it alone. Fill Actual Cost in as invoices, payroll, and tickets arrive.
Cost Code | Estimated Cost | Actual Cost | Variance $ | Variance % | Notes | Rank key (helper)
Asphalt Material
Aggregate Base
Trucking
Field Labor
Foreman / Supervision
Paver
Rollers
Skid Steer
Milling
Saw Cutting
Excavation / Demo
Disposal
Tack / Emulsion
Sealcoat Material
Crack Seal Material
Striping Material
Traffic Control
Concrete
Rentals
Subcontractors
Mobilization
Project Management
Permits / Fees
Miscellaneous
TOTAL DIRECT JOB COST
Job Financial Summary
Contract Revenue |  | Pulled from Project Summary > Revenue (Actual), which defaults to the contract amount.
Estimated Direct Cost
Actual Direct Cost
Total Cost Variance |  | Positive means the job cost more than estimated.
Estimated Gross Profit
Actual Gross Profit
Estimated Gross Margin %
Actual Gross Margin %
Gross profit = revenue - direct job cost. Gross margin % = gross profit / revenue. These figures are gross margin against revenue, not markup on cost, and they do not deduct company overhead.
Shaded cream = you enter this. Shaded grey = calculated, don't overtype.
Need more cost codes? Rows 4-33 are all inside the totals, so use the spare rows or insert a row anywhere between them and the totals follow.

## Paving Production
Paving Production - Estimate vs. Actual
Financial cost codes alone rarely explain a miss. Production data is where the reason usually shows up.
Metric | Estimated | Actual | Variance | Notes
Asphalt Tons |  |  |  | Estimated tonnage vs. tons actually purchased.
Asphalt Price / Ton |  |  |  | Quoted plant or delivered price per ton.
Material Cost / Ton |  |  |  | Effective cost per ton from the Asphalt Material cost code. Compare against the quoted price above.
Paving Hours |  |  |  | Hours the paver was actually placing material.
Tons / Paving Hour |  |  |  | Asphalt tons / paving hours.
Total Crew Hours |  |  |  | All field labor hours charged to the job.
Labor Hours / Ton |  |  |  | Total crew hours / asphalt tons.
Number of Trucks
Truck Hours |  |  |  | Include waiting time at the plant and on site.
Truck Cost |  |  |  | Pulled from the Trucking cost code.
Trucking Cost / Ton |  |  |  | Truck cost / asphalt tons.
Number of Loads
Average Truck Payload |  |  |  | Asphalt tons / number of loads.
Mobilizations |  |  |  | Count every trip out, not just the first.
Milling Hours
Milling SF
Paving SF
Paving Days
Overtime Hours
Equipment Downtime Hours |  |  |  | Hours production stopped waiting on equipment.
Rework Hours |  |  |  | Work performed twice. Keep it out of general labor hours.
Shaded cream = you enter this. Shaded grey = calculated, don't overtype.
Ratios stay blank until the inputs they depend on are filled in, so a partly-completed sheet never shows a divide-by-zero error.

## Variance Analysis
Why Did the Job Miss the Estimate?
The cost codes say where. This sheet is where you record why, and what the estimator should do differently next time.
Primary Variance Cause
Secondary Variance Cause
Estimating Database Update Required?
Root Cause
Why did this happen — the underlying operational reason, not the cost code.
What Happened?
The sequence of events on the project.
What Should Change in Future Estimates?
The specific estimating assumption to revise.
Recommended Estimating Change
For example: increase trucking cycle assumption, add a second mobilization, lower the handwork production rate.
Record what actually happened before deciding what to change. A cost code that ran over is a symptom; the estimating assumption behind it is the thing worth fixing.

## Job Cost Report
Project Job Cost Report
A one-page management summary. Everything on this sheet is pulled from the other tabs — print it as-is.
Project Information
Project
Client
Contract Amount
Start Date
Completion Date
Estimator
Project Manager
Financial Summary
Estimated Direct Cost
Actual Direct Cost
Cost Variance
Estimated Gross Profit
Actual Gross Profit
Estimated Gross Margin
Actual Gross Margin
Production Summary
Estimated Tons
Actual Tons
Estimated Tons / Hour
Actual Tons / Hour
Estimated Labor Hours
Actual Labor Hours
Estimated Truck Hours
Actual Truck Hours
Estimated Paving Days
Actual Paving Days
Largest Cost Variances
Rank | Cost Code | Variance $ | Variance %
1
2
3
Ranked by dollar variance across the cost codes. A negative figure means that code came in under the estimate.
Lessons Learned
Future Estimate Adjustments
General contractor-management tool. Not accounting, tax, or financial advice.

## Instructions
How to Use This Workbook | Project types (list source) | Variance causes (list source) | Database update (list source)
Free paving contractor job costing spreadsheet from The Pavement Directory. | Asphalt Paving | Asphalt Material Overrun | Yes
| Asphalt Repair | Incorrect Tonnage Estimate | No
1. Enter project data | Mill & Fill | Trucking Delay | Review Needed
Fill in the Project Summary sheet: project, client, estimator, project manager, contract amount, dates, and project type. The contract amount feeds every profit and margin calculation in the workbook. | Overlay | Plant Delay
| Sealcoating | Traffic
| Crack Sealing | Crew Production
2. Enter estimated costs | Striping | Equipment Downtime
On Estimate vs Actual, enter the original estimate for each cost code — what the estimator assumed before the job started. Do not revise these later because the actual came in differently; the whole point is preserving the original assumption. | Concrete | Unexpected Handwork
| ADA Improvements | Additional Mobilization
| Drainage | Weather
3. Enter actual costs as the project progresses | Other | Base Failure
Fill the Actual Cost column in as invoices, payroll, material tickets, and equipment hours arrive. Variance dollars and percentages calculate themselves. |  | Unexpected Excavation
Scope Change
Rework
4. Record production |  | Disposal Overrun
On Paving Production, enter tons, paving hours, crew hours, truck hours, loads, mobilizations, and paving days for both the estimate and the actual. Tons per hour, labor hours per ton, trucking cost per ton, and average payload are calculated. |  | Rental Equipment
Overtime
Traffic Control
5. Review variances |  | Scheduling
Look at the cost codes with the largest dollar and percentage variances, then check whether the production numbers explain them. |  | Subcontractor Overrun
Other
6. Complete the variance analysis
On Variance Analysis, record the primary and secondary causes, what actually happened, and what should change in future estimates.
7. Print the Job Cost Report
The Job Cost Report sheet is a one-page printable summary that pulls from every other sheet. It is already set to fit one page wide.
8. Update your estimating assumptions
Feed what you learned back into the next estimate. That feedback loop is what job costing is actually for.
Cells shaded cream are for your input. Cells shaded grey are calculated — overtyping one replaces a formula. Rows 4 through 33 on Estimate vs Actual all sit inside the totals, so you can rename the preloaded cost codes, use the spare rows, or insert rows between them without breaking the totals.
This workbook is a general contractor-management tool and is not accounting, tax or financial advice. Contractors should adapt cost codes and financial treatment to their own accounting systems.
thepavementdirectory.com/contractor-resources/construction-job-costing-spreadsheet/